## Milestones
Property Address:
545 1st Street N, Minneapolis MN
No. | Milestone | Start Date | End Date | Budget | Actuals | Manager | Email/website | Phone | Username/password | Start Date | End Date | Budget | Manager | Email/website | Start Date | End Date | Budget | Manager | Department
1 | Execute PA |  | 2013-05-28 |  |  | President |  |  |  | 0 | 2013-05-28 | 0 | President | 0 | 0 | 0 | 0 | President | 0
2 | Create Loan Requisition Spreadsheet |  | 2013-05-28 |  |  | President
3 | Open Binder, folders, sales checklist and sales agent checklist |  | 2013-05-28 |  |  | Manager
4 | Record on LoneWolf |  | 2013-05-28 |  |  | Manager |  |  | 500/ekungba
5 | Record on www.uniteddevelopersllc.com as 1. acquisition, and 2. as under construction. Under construction should reflect expected sales price, and expected property details |  | 2013-05-28 |  |  | Manager
6 | Update Properties Profit Spreadsheet |  | 2013-05-28 |  |  | Manager
7 | Order for Insurance binder |  |  |  |  | Manager | Steve Juvland/sjuv@horniginsurance.com
8 | Order for Schematic (Architectural) drawings from igreendesigns |  | N/A
9 | Order Energy Audit |  | 2013-05-28 |  |  | Manager | simonsonenergy@comcast.net | 6122277694
10 | Order Virtual Tour - Take pictures before. Note: Home site still plus for pre construction and silver for post construction |  | 2013-05-28 |  |  | Manager | http://obeo.com/ |  | abadewas / ekungba
11 | Order Engineering Inspection and drawings |  | N/A |  |  | President | Doug Hughes <drhughes58@gmail.com>; | 952-393-4360 |  | 0 | N/A | 0 | President | Doug Hughes <drhughes58@gmail.com>; | 0 | #VALUE! | 0 | President | Doug Hughes <drhughes58@gmail.com>;
12 | *Install Radon Tests & pick up 4 days later* |  | N/A |  |  | Manager
13 | Call for radon mitigation quote if higher than 4.0pCi/L |  | N/A |  |  | Manager | Home Safety Solutions Inc. <info@homesafetysolutionsinc.com>; | 612-490-1296
14 | *Schedule Lead Test & follow up regularly for results* |  | N/A |  |  | Manager | Form to Michael.A.Jensen@co.hennepin.mn.us <Michael.A.Jensen@co.hennepin.mn.us>; | 6123660965
15 | Close on Property |  | 2013-05-28 |  |  | President
16 | Order *City Of Brooklyn Park/other cities Pre-construcion Inspection * |  | N/A |  |  | President | E-mail Abigail:Abigail.Shafer@brooklynpark.org | 763-488-6384 |  | 0 | N/A | 0 | President | E-mail Abigail:Abigail.Shafer@brooklynpark.org | 0 | #VALUE! | 0 | President | E-mail Abigail:Abigail.Shafer@brooklynpark.org
17 | Call for utilities |  | 2013-05-28 |  |  | Manager | centerpointenergy.com/eXcelenergy |  | abadewas/ekunga03
18 | Order Installation of Posts |  | N/A |  |  | Manager | http://www.continentalpostservices.com | 763-746-1388 | adeyinka.badewa/adeyinka
19 | Regularly update www.uniteddevelopersllc.com with construction progress |  | 2013-05-28 |  |  | Manager |  |  | admin/@admin123
20 | Record on QuickBooks, and regular update Units, united (update Bills, Invoices and Assets/Liabiities) |  | 2013-05-28 |  |  | Manager |  |  | ekungba
21 | Update Properties Profit Spreadsheet |  | 2013-05-28 |  |  | Manager
22 | Regularly Update Draw Requests, and as needed |  | N/A |  |  | Manager
23 | Regularly obtain draw Requests from the city |  | N/A |  |  | Manager
24 | Obtain City Permits |  | N/A |  |  | President |  |  |  | 0 | N/A | 0 | President | 0 | 0 | #VALUE! | 0 | President | 0
25 | Hires Subcontractors |  | 2013-05-28 |  |  | President |  |  |  | 0 | 2013-05-28 | 0 | President | 0 | 0 | 0 | 0 | President | 0
26 | Obtain General Liability Insurance from subs |  |  |  |  | Manager
27 | Obtain Dumpster |  | N/A |  |  | President | Alpha Dumpster/Nancy | 9524327616 |  | 0 | N/A | 0 | President | Alpha Dumpster/Nancy | 0 | #VALUE! | 0 | President | Alpha Dumpster/Nancy
28 | Order for Demolition |  | N/A |  |  | President | N.A.S.A. LLC./Sergey/Arthur | 6512359019/6512788724 |  | 0 | N/A | 0 | President | N.A.S.A. LLC./Sergey/Arthur | 0 | #VALUE! | 0 | President | N.A.S.A. LLC./Sergey/Arthur
29 | Call for Radon mitigation installation |  | N/A |  |  | President | Home Safety Solutions Inc. <info@homesafetysolutionsinc.com>; | 612-490-1296 |  |  | N/A |  | President |  |  | #VALUE! |  | President
30 | Call for engineers if necessary after demolition |  | N/A |  |  | President | Doug Hughes <drhughes58@gmail.com>; | 952-393-4360 |  | 0 | N/A | 0 |  |  | 0 | #VALUE! | 0
31 | Order for Window Installation |  | N/A |  |  | President |  |  |  | 0 | N/A | 0 | President | 0 | 0 | #VALUE! | 0 | President | 0
32 | Order for Framing |  | N/A |  |  | President |  |  |  | 0 | N/A | 0 | President | 0 | 0 | #VALUE! | 0 | President | 0
33 | Order for Roofing |  | N/A |  |  | President |  |  |  | 0 | N/A | 0 | President | 0 | 0 | #VALUE! | 0 | President | 0
34 | Order for cabinets measurements |  | N/A |  |  | President |  |  |  | 0 | N/A |  | President |  | 0 | #VALUE! |  | President
35 | Order for millwork measurements |  | 2013-05-28 |  |  | President |  |  |  | 0 | 2013-05-28 |  | President |  | 0 | 0 |  | President
36 | Purchase Initial Inventory, millwork, cabinets, appliances, plumbing |  | 2013-05-28 |  |  | President |  |  |  | 0 | 2013-05-28 | 0 | President | 0 | 0 | 0 | 0 | President | 0
37 | Call for landscaping |  | N/A |  |  | President
38 | Receive Stock |  | 2013-05-28 |  |  | President |  |  |  | 0 | 2013-05-28 | 0 | President | 0 | 0 | 0 | 0 | President | 0
39 | Order for Plumbing Rough in |  | 2013-05-28 |  |  | President |  |  |  | 0 | 2013-05-28 | 0 | President | 0 | 0 | 0 | 0 | President | 0
40 | Order for Electricals Rough in |  | N/A |  |  | President |  |  |  | 0 | N/A | 0 | President | 0 | 0 | #VALUE! | 0 | President | 0
41 | Order for City Rough In Inspection |  | N/A |  |  | President |  | 7634886379 |  | 0 | N/A | 0 | President | 0 | 0 | #VALUE! | 0 | President | 0
42 | Drywall, and First Coat of Painting |  | 2013-05-28 |  |  | President |  |  |  | 0 | 2013-05-28 | 0 | President | 0 | 0 | 0 | 0 | President | 0
43 | Order for Flooring |  | N/A |  |  | President |  |  |  | 0 | N/A | 0 | President | 0 | 0 | #VALUE! | 0 | President | 0
44 | Call for measurements of carpet |  | 2013-05-28 |  |  | President | [6 empty] | President |  |  |  |  | President
45 | Call for Millwork Installation |  | N/A |  |  | President |  |  |  | 0 | N/A | 0 | President | 0 | 0 | #VALUE! | 0 | President | 0
46 | Call for Countertop installation |  | N/A |  |  | President |  |  |  | 0 | N/A | 0 |  |  | 0 | #VALUE! | 0
47 | Call for Electrical Finish |  | 2013-05-28 |  |  | President |  |  |  | 0 | 2013-05-28 | 0 | President | 0 | 0 | 0 | 0 | President | 0
48 | Call for Plumbing finish |  | 2013-05-28 |  |  | President |  |  |  | 0 | 2013-05-28 | 0 | President | 0 | 0 | 0 | 0 | President | 0
49 | Call for Carpet installation |  | 2013-05-28 |  |  | President |  |  |  | 0 | 2013-05-28 | 0 | President |  | 0 | 0 | 0 | President
50 | Call for vents and ducts cleaning |  | N/A |  |  | Manager | Allied Ducts & Vents Cleaning | 6514817005 |  |  |  |  | Manager |  |  |  |  | Manager
51 | Check on Landscaping |  | N/A |  |  | President |  |  |  | 0 | N/A | 0 | President | 0 | 0 | #VALUE! | 0 | President | 0
52 | Call for City Inspection - post +building permits inspection |  | N/A |  |  | President |  | 7634886379 |  |  | N/A |  |  |  |  | #VALUE!
53 | Virtual Tours - After (Silver with Obeo) |  | 2013-05-28 |  |  | Manager | http://obeo.com/ |  | abadewas / ekungba
54 | Measurements of property |  | 2013-05-28 |  |  | President
55 | Open Listing File/Check Agents Listing Checklist and Listing Checklist |  | 2013-05-28 |  |  | Manager
56 | List on Mls |  | 2013-05-28 |  |  | Manager | https://idp.northstarmls.com/idp/Authn/UserPassword |  | 502016640/ekungba03
57 | Record on LoneWolf |  | 2013-05-28 |  |  | Manager
58 | Update on Mls.com/BookAShowing.com |  | 2013-05-28 |  |  | Manager
59 | Place lockbox in the house and fill out lockbox checkout |  | 2013-05-28 |  |  | Manager
60 | List on www.Uniteddevelopersllc.com |  | 2013-05-28 |  |  | Manager | www.uniteddevelopersllc.com/admin |  | admin/@admin123
61 | Update Properties Profit Spreadsheet |  | 2013-05-28 |  |  | Manager
62 | Make Property Profile Summary and make copies for house |  |  |  |  | Manager
63 | Make Property Profile Book |  |  |  |  | Manager
64 | Regularly Pay soft costs like utility bills, taxes |  | 2013-05-28 |  |  | Manager |  |  |  | 0 | 2013-05-28 | 0 | Manager | 0 | 0 | 0 | 0 | Manager | 0
65 | Sell Property/Offer Accepted |  | 2013-05-28 |  |  | President |  |  |  | 0 | 2013-05-28 | 0 | President | 0 | 0 | 0 | 0 | President | 0
66 | Record Sales on LoneWolf |  | 2013-05-28 |  |  | Manager
67 | Update MLS to pending |  | 2013-05-28 |  |  | Manager | https://idp.northstarmls.com/idp/Authn/UserPassword |  | 502016640/ekungba03
68 | Update www.uniteddevelopersllc.com to pending |  | 2013-05-28 |  |  | Manager
69 | Update Properties Profit Spreadsheet |  | 2013-05-28 |  |  | Manager
70 | Property Closes |  | 2013-06-17 |  |  | President
71 | Update mls to sold |  | 2013-06-17 |  |  | Manager
72 | Update www.uniteddevelopersllc.com to sold |  | 2013-06-17 |  |  | Manager
73 | Update Properties Profit Spreadsheet |  | 2013-06-17 |  |  | Manager
74 | Return lockbox and update lockbox check-out and check-in |  |  |  |  | Manager
75 | Review Agents and Listing Check list |  | 2013-06-17 |  |  | Manager
76 | Update Lonewolf |  |  |  |  | Manager |  |  | 500/ekungba
77 | Remove posts |  | N/A |  |  | Manager | http://www.continentalpostservices.com | 763-746-1388 | adeyinka.badewa/adeyinka
78 | Get final bills from utilities and update Bills Pay with auto and View |  |  |  |  | Manager
79 | Update QuickBooks, and regular update Units, united (update Bills, Invoices and Assets/Liabiities)/Schedule Payment with WellsFargo/lien waivers/Contracts |  |  |  |  | Manager |  |  | ekungba
80 | Update Final Draw Request |  |  |  |  | Manager
81 | Reimburse from the City |  |  |  |  | President
82 | Update QuickBooks |  |  |  |  | Manager
83 | Update Properties Profit Spreadsheet |  |  |  |  | Manager |  |  |  | 0 | 0 | 0 | Manager | 0 | 0 | 0 | 0 | Manager | 0
| Totals |  |  | 0 | 0 | [6 empty] | 0 |  |  |  |  | 0

## QuickBooks Entry
QUICK BOOKS ENTRY
INVOICES - UNITED
Enter invoices on Bills
Pay Invoices if Paid
Issue checks Store payments
Enter Bills and Invoices on Invoices
Enter Invoices and Bills an Loan Requisition
Compare Invoice amount on QB to column Total on Loan Requisition
Check on PL by Job, should be zero, excpt for Contractor fee
INVOICES - UNITED
Enter Utilities / Maintenance on Bills
Pay Utility / Maintenance invoices if paid
Schedule on Wellls Fargo if Utility or maintenance not paid
Enter as Bills to Units of Invoice total/hard cost total from units
Create Invoice: Enter Utility and maintenance costs on Invoice on United
Same Invoice: Enter the total amount from Units
Compare Invoice Total to total on Loan acquisition and Rehab
Check on PL by Job, should be zero
Create entry Total on Invoice to Rehab costs and Shareholder loan or City or loan company
Check on Balance Sheet: Total Rehab costs should equal to shareHolder Loan + Creditors
Draw Request
Enter on Draw Request total on United Invoices
Make copy of all invoices on United
Make copy of Loan Requisition
Both Draw Request and Loan Requisition and United Invoice should be same
Payment Received