## Construction Status
Property Address:
7021 137th Avenue NW, Ramsey MN 55303
No. | Milestone | Start Date | End Date | Comments
1 | Update on www.Uniteddevelopersllc.com
2 | Order for Schematic (Architectural) drawings
3 | Order Energy Audit
4 | Order Virtual Tour
5 | Order Engineering Inspection and drawings
6 | *Install Radon Tests & pick up 4 days later
7 | Call for radon mitigation quote if higher than 4.0pCi/L
8 | Schedule Lead Test & follow up regularly for results for properties built before 1978
9 | Close on purchase of Property
10 | Order for City Pre-construcion Inspection
11 | Install RE/MAX Post
12 | Obtain City Permits
13 | Order for Demolition
14 | Call for Radon mitigation installation
15 | Call for engineers if necessary after demolition
16 | Windows
17 | Farming
18 | Roofing
19 | landscaping
20 | Plumbing Rough in
21 | Electricals Rough in
22 | Electrical Rough in Inspection
23 | City Rough In Inspection
24 | Drywall, and First Coat of Painting
25 | Millwork Installation
26 | Countertop installation
27 | Electrical Finish
28 | Plumbing finish
29 | Carpet installation
30 | Vents and ducts cleaning
31 | Electrical Final Inspection
32 | City Inspection - post +building permits inspection
33 | Virtual Tours - After (Silver with Obeo)
34 | Measurements of property
35 | List on Mls
36 | Place lockbox in the house and fill out lockbox checkout
37 | Update on www.Uniteddevelopersllc.com to Active
38 | Sell Property/Offer Accepted
39 | Update MLS to pending
40 | Update www.uniteddevelopersllc.com to pending
41 | Property Closes
42 | Update mls to sold
43 | Update www.uniteddevelopersllc.com to sold
44 | Take out lock box
45 | Review Agents and Listing Check list
46 | Remove posts
47 | Get final bills from utilities
Totals